## Sheet1
Code | Project Name | Project Owner | Project Description | Project Task Owner | Project Task Name | Start Date | End Date | Completion Date | Type
RYD-007 | Project - 1 | Person-1 | To repaint the wall outside the x area | Person-3, Person-8 | Subtask 1 | 2023-06-07 | 2023-06-07 | 2023-06-18 | Non Construction
RYD-007 | Project - 1 | Person-1 | To repaint the wall outside the x area | Person-2 | Subtask 2 | 2023-06-08 | 2023-06-08 | 2023-06-18 | Non Construction
RYD-007 | Project - 1 | Person-1 | To repaint the wall outside the x area | Person-3, Person-2 | Subtask 3 | 2023-06-11 | 2023-06-11 | 2023-06-18 | Non Construction
RYD-007 | Project - 1 | Person-1 | To repaint the wall outside the x area | Person - 1 | Subtask 4 | 2023-06-11 | 2023-06-20 | 2023-06-20 | Non Construction
RYD-007 | Project - 1 | Person-1 | To repaint the wall outside the x area | Person-3 | Subtask 5 | 2023-06-15 | 2023-06-20 | 2023-06-20 | Non Construction
RYD-007 | Project - 1 | Person-1 | To repaint the wall outside the x area | Person-8 | Subtask 6 | 2023-07-12 | 2023-07-12 | 2023-08-22 | Non Construction
RYD-007 | Project - 1 | Person-1 | To repaint the wall outside the x area | Person-3 | Subtask 7 | 2023-07-12 | 2023-07-12 | 2023-07-12 | Non Construction
RYD-007 | Project - 1 | Person-1 | To repaint the wall outside the x area | Person-3, Person-2 | Subtask 8 | 2023-07-01 | 2023-07-15 | 2023-07-12 | Non Construction
RYD-007 | Project - 1 | Person-1 | To repaint the wall outside the x area | Person-8 | Subtask 9 | 2023-07-15 | 2023-07-30 | 2023-09-20 | Non Construction
RYD-007 | Project - 1 | Person-1 | To repaint the wall outside the x area | Person-2 | Subtask 10 | 2023-07-23 | 2023-08-01 | 2023-09-20 | Non Construction
RYD-007 | Project - 1 | Person-1 | To repaint the wall outside the x area | Person-2 | Subtask 11 | 2023-08-01 | 2023-08-07 | 2023-09-20 | Non Construction
RYD-007 | Project - 1 | Person-1 | To repaint the wall outside the x area | Person-3, Person-2 | Subtask 12 | 2023-08-07 | 2023-08-14 | 2023-09-20 | Non Construction
RYD-007 | Project - 1 | Person-1 | To repaint the wall outside the x area | Person-2 | Subtask 13 | 2023-08-01 | 2023-08-15 |  | Non Construction
RYD-007 | Project - 1 | Person-1 | To repaint the wall outside the x area | Person-3, Person-2 | Subtask 14 | 2023-08-14 | 2023-08-21 |  | Non Construction
RYD-007 | Project - 1 | Person-1 | To repaint the wall outside the x area | Person-3, Person-1 | Subtask 15 | 2023-08-21 | 2023-09-01 | 2023-09-20 | Non Construction
RYD-007 | Project - 1 | Person-1 | To repaint the wall outside the x area | Person-8 | Subtask 16 | 2023-08-21 | 2023-09-01 |  | Non Construction
RYD-007 | Project - 1 | Person-1 | To repaint the wall outside the x area | Person-3 | Subtask 17 | 2023-08-21 | 2023-09-01 |  | Non Construction
RYD-007 | Project - 1 | Person-1 | To repaint the wall outside the x area | Person-3, Person-2 | Subtask 18 | 2023-08-21 | 2023-09-15 |  | Non Construction
RYD-007 | Project - 1 | Person-1 | To repaint the wall outside the x area | Person-3, Person-8 | Subtask 19 | 2023-08-21 | 2023-09-15 |  | Non Construction
RYD-007 | Project - 1 | Person-1 | To repaint the wall outside the x area | Person-3, Person-1 | Subtask 20 | 2023-10-01 | 2023-10-01 |  | Non Construction